## Q2.2022
Week | Back End | Dificulity
2022-05-30 | Project: Create Github repository | Easy
| Project: Create a spreadsheet for estimate project plan | Medium
| Project: Create a trello board for task tracking | Easy
2022-06-06 | CI: Go to Azure cloud shell and clone project | Easy
| CI: Create a Makefile | Easy
| CI: Create a requirements.txt file | Easy
| CI: Create python virtual eviroment | Easy
2022-06-13 | CI: Create app file and test file | Medium
| CI: Enable Github Actions | Medium
| CI: Update yml code | Medium
| CI: Testing remote test pass | Medium
2022-06-20 | CD: Building continuos delivery on Azure | Medium
| CD: Making predictions | Easy
| Project: Document README file | Medium
| Project: Make a video demo | Hard
Goals
Submit project 2
Q3.2022 | Complete udacity course Azure DevOps using Azure
Yearly plan | Update and maintain to make sure the code still working